## Risk Assesment
|  |  |  | Risk assessment for supplier : |  |  | HAYNES INTERNATIONAL, UK
Risk Assessment Format | [11 empty] | Format No | FM 71211 Rev 01
[12 empty] | Date | 2014-10-30
Sr No | Process | Type of risk | Risk Identified | Entry level Risk Analysis |  | RPN1 | Controls Available / Mitigation program | Responsible for implementation | Time frame for implementation | Implementation status | Residual risk Analysis |  | RPN2 | Risk Accepatble/ Not acceptable | Remarks (if any)
|  |  |  | Likelihood1 | Consequence1 | L1 X C1 |  |  |  |  | Likelyhood2 | Consequence2 | L2 X C2
1 | Financial condition | Close down of business | Material ordered will not be supplied, dispatch delay | 1 | 3 | 3 | Since listed company, financial data available on Internet. Even customers have approved this vendor. We have alternate vendors available in case of failure in material supply | Divyesh | By Dec 24 | In Process | 1 | 2 | 2 | A | -
2 | Operational Risk | Overloading of resources | Delay in receipt of material from supplier | 2 | 3 | 6 | Based on the supplier capacity, selective materials will be planned for ordering | Divyesh | By Jan 24 | Complete | 1 | 2 | 2 | A | -
3 | Compliance | Non-Compliance to latest standards/approvals | Suppliers will fall short of meeting the latest quality standards, resulting in the supply of non-compliant materials. | 2 | 4 | 8 | On an quaterly basis evaluate the supplier's compliance with relevant industry standards. | Divyesh | By March 25 | In Process | 2 | 1 | 2 | A | Consult with customer for case to case approval.
4 | Business | Competition | Supplier may start working with GPS competitors | 3 | 1 | 3 | Being a distributor, develop alternate supplier for the required grade of material which we have as per approved vendor list | Divyesh | By March 25 | Complete | 1 | 1 | 1 | A | -
5 | Sub tier lead time | Supply chain delay | Ordered material will not be available on time resulting in project delay | 3 | 1 | 3 | Explore alternate vendors who can supply these raw materials, | Divyesh | By Feb 24 | Complete | 2 | 1 | 2 | A | -
6 | Network Failure | Disruption in communication | Non receipt of communication resulting in supply delay / stock out situation | 3 | 2 | 6 | Weekly communication with vendor (phone/email) to get order updates | Divyesh | By Jan 24 | Complete | 1 | 2 | 2 | A | -
7 | Geopolitical Tensions | Supply chain disruption | Production delays, shortages of critical materials, increased costs, and potential impacts on project timelines and delivery schedules. | 3 | 2 | 6 | Russia Ukraine Crisis and Isreal Iran war / Sanctions put in place by US / EU, entire supply chain disruption, Exploring alternate vendors who can supply required material to fulfill project demand | Divyesh | By Dec 24 | In Process | 2 | 2 | 4 | A | We are exploring alternate vendors to get material as per our requirement
Approved BY
| Prepared by : | Divyesh Kanchan | [8 empty] | Date :
| Date : | 2024-07-19 | [7 empty] | Reviewed on | Date : | 2024-07-19
| Likelihood |  | Consequence
1 | So far not occurred | 1 | Nil or no consequence | [6 empty] | Notes : | Alternate distributors are available and can supply the materials
2 | In new projects some time possible | 2 | Tolerable Financial consequence
3 | In all projects possibility is there | 3 | Financial trouble and planning collapse
4 | Already multiple times occurred | 4 | Operational and competency(feasibility) problems
5 | In all types of projects faced the difficulty | 5 | Organization image and large scale finance related business problems
RISK REVIEW RECORDS
| Review OPEN Risks and Progress on Planned Action with SBU Head and Rocord Findings RVU Freqency: For RPN> 15 - Monthly For RPN>6 but <12 - Quarterly |  |  |  |  | Risks with RPN LESS THAN 5 may be 'ACCEPTED', with approval from concerned SBU Head, Unless put under ' Watched' Category when having anticipated potential to turn into higher RPN Accepted risks must be reviewed periodically (at least quarterly to ensure |  |  |  |  | 5 | 5 | 10 | 15 | 20 | 25
[11 empty] | 4 | 4 | 8 | 12 | 16 | 20
[11 empty] | 3 | 3 | 6 | 9 | 12 | 15
[11 empty] | 2 | 2 | 4 | 6 | 8 | 10
[11 empty] | 1 | 1 | 2 | 3 | 4 | 5
[12 empty] | 1 | 2 | 3 | 4 | 5